## Records Progress
Department/Division | Scheduled | Discover | Retention Schedule |  |  | Disposal Catchup | Design | Configure & Deploy | Training | Go Live | Backfiling
Department/Division |  |  | Internal Review | Records Commission | Historical Society | [5 empty] | total boxes | boxes completed | Pct complete
Council Office | 2015 | X | X | 2015-12-10 | 2016-01-07 |  | X | X | X | X | 59 | 39 | 66.1%
General (all) |  |  |  | 2016-06-14
City Attorney |  |  |  | 2016-06-14 | [6 empty] | 26 | 0 | 0%
Mayor's Court |  |  | X | 2016-01-12 | 2016-02-05
Public Service & Engineering | 2016 |  |  | 2016-01-12 | [6 empty] | 185 | 0 | 0%
Administrative Division |  | X | X | 2016-01-12 | 2016-02-05 | [5 empty] | 25 | 0 | 0%
Engineering Division |  | X | X | 2016-01-12 | 2016-02-05 | X |  |  |  |  | 127 | 0 | 0%
Facility Maintenance Division |  | X | X | 2016-01-12 | 2016-02-05
Fleet Division |  | X | X | 2016-01-12 | 2016-02-05 | X
Sanitary Division |  | X | X | 2016-01-12 | 2016-02-05
Stormwater Division |  | X | X | 2016-01-12 | 2016-02-05
Streets Division |  | X | X | 2016-01-12 | 2016-02-05
Utility Billing Division |  | X | X | 2016-01-12 | 2016-02-05 | [5 empty] | 15 | 0 | 0%
Water Division |  | X | X | 2016-01-12 | 2016-02-05 | X |  |  |  |  | 18 | 0 | 0%
Zoning Division |  |  |  | 2016-06-14
Building Division |  | 2016-05-12 |  | 2016-06-14
Parks & Recreation |  |  |  | 2016-06-14
Finance |  |  |  | 2016-09-13
Tax |  |  |  | 2016-09-13
Payroll |  |  |  | 2016-09-13 | [6 empty] | 43 | 0 | 0%
Human Resources | 2016 | X |  | 2016-06-14 |  |  | X |  |  |  | 69 | 0 | 0%
Civil Service* |  |  |  | 2016-06-14 | [6 empty] | 17 | 0 | 0%
Mayor's Office |  |  |  | 2016-09-13
Public Information Manager |  |  |  | 2016-09-13
Information Technology |  |  |  | 2016-06-14 | [6 empty] | 0 | 0
Planning & Development |  |  |  | 2016-09-13
Police | 2015 | X | X | 2015-12-10 | 2016-01-07 |  | X | X | X | X | 170 | 90 | 52.94%
*final destination tbd

## Definitions
Project Phase |  | Description
Discover |  | Document and confirm current records process Identify business goals Identify indexes, subfolders, document descriptions
Retention Schedule | Internal Review | Department updates records retention schedule with the help of Council Office
| Records Commission | Records commission approves revised retention schedule (quarterly meetings)
| Historical Society | Ohio Historical Society approves revised retention schedule Revised schedule is effective
Disposal Catchup |  | Once retention schedule is approved, dispose of all records whose retention period has expired prior to system deployment & backfiling
Design |  | Develop and build application Test
Configure & Deploy
Train |  | Vendor provides training to department users
Go Live |  | Department staff implement electronic records process
Backfile |  | Vendor scans and indexes boxes of inactive records

## Intellivue Box Quote
INTELLIVUE INITIALLY QUOTED BOX COUNTS VS. ACTUAL
Department/Division | total boxes quoted to Intellivue | total boxes expected | actual total boxes backfiled
Council Office | 43 | 103 | 23
Microfilm | 16 | 16 | ?
City Attorney | 26 | 26
Engineering | 127 | 127
Public Service | 25 | 25
Utility Billing Division | 15 | 15
Water Division | 18 | 18
Zoning Division | 0 | 5
Building Division | 0 | 15
Parks & Recreation | 0 | 0
Payroll | 43 | 43
Human Resources | 72 | 72
BWC | 6 | 6
Civil Service | 17 | 17
Mayor's Office | 0 | 0
Information Technology | 0 | 0
Planning & Development | 0 | 0
Police | 250 | 170 | 90
TOTAL | 658 | 658 | 113
|  | Box Count to fluctuate to meet quote | Box Count still to backfile
|  | 0 | 545

## box counts
updated: 5-12-2016
ONSITE BOX COUNT |  | OFFSITE BOX COUNT |  | IN PROGRESS BOX COUNT |  | ALL BOX COUNT
BOX COUNT | DEPARTMENT | BOX COUNT | DEPARTMENT | BOX COUNT*estimate | DEPARTMENT | BOX COUNT | DEPARTMENT
17 | Council | 51 | Council | 8 | Council | 76 | Council
11 | Court | 190 | Court | 0 | Court | 201 | Court
4 | Development | 241 | Development | 21 | Development | 266 | Development
76 | Finance | 43 | Finance | 25 | Finance | 144 | Finance
140 | Human Resources | 23 | Human Resources | 15 | Human Resources | 178 | Human Resources
0 | Information Technology | 0 | Information Technology | 0 | Information Technology | 0 | Information Technology
1 | Legal | 0 | Legal | 5 | Legal | 6 | Legal
0 | Mayor's Office | 2 | Mayor's Office | 2 | Mayor's Office | 4 | Mayor's Office
71 | Parks & Recreation | 3 | Parks & Recreation | 9 | Parks & Recreation | 83 | Parks & Recreation
0 | Police Department | 16 | Police Department | 0 | Police Department | 16 | Police Department
12 | Service | 0 | Service | 44 | Service | 56 | Service
166 | Service-Building *bag=box | 0 | Service-Building | 19 | Service-Building | 185 | Service-Building
52 | Service-Engineering | 1 | Service-Engineering | 3 | Service-Engineering | 56 | Service-Engineering
4 | Service-Water | 0 | Service-Water | 22 | Service-Water | 26 | Service-Water
4 | Service-Zoning | 0 | Service-Zoning | 10 | Service-Zoning | 14 | Service-Zoning
558 | TOTAL ONSITE | 570 | TOTAL OFFSITE | 183 | TOTAL IN PROGRESS | 1311 | TOTAL BOXES
*does not include INPROGRESS
*onsite = basement storage
DISPOSED OF BOX COUNT BY DEPARTMENT/DIVISION
BOX COUNT | DEPARTMENT
48 | Council |  |  | Note: Development may include Building (now Service) boxes as they are labeled "DV"
42 | Court
2 | Development
9 | Finance
12 | Human Resources
3 | Information Technology
8 | Legal
3 | Mayor's Office
47 | Parks & Recreation
10 | Police Department
110 | Service
25 | Service-Building *bag=box
0 | Service-Engineering
31 | Service-Water
0 | Service-Zoning | 438
350 | TOTAL BOXES DISPOSED in 2016 TO DATE | 2016 PREDITION FOR DISPOSED TOTAL

## disposed of boxes
UPDATED: 5/12/16
DISPOSED OF BOX COUNT BY DEPARTMENT/DIVISION
BOX COUNT | DEPARTMENT
48 | Council
42 | Court
2 | Development
9 | Finance
12 | Human Resources
3 | Information Technology
8 | Legal
3 | Mayor's Office
47 | Parks & Recreation
10 | Police Department
110 | Service
25 | Service-Building *bag=box
0 | Service-Engineering
31 | Service-Water
0 | Service-Zoning |  | 449
350 | TOTAL BOXES DISPOSED in 2016 TO DATE |  | 2016 PREDITION FOR DISPOSED TOTAL
DISPOSED OF BOX COUNT BY DATE
BOX COUNT (estimate) | DEPARTMENT | DATE
30 | Council | 2016-01-01
6 | Parks | 2016-01-02
12 | HR/CSC | 2016-01-07
1 | Finance | 2016-01-08
30 | Court | 2016-01-15
8 | Council/PC | 2016-02-01
10 | Police Department | 2016-02-01
6 | Parks | 2016-02-03
2 | Building | 2016-02-23
8 | Legal | 2016-03-01
8 | Finance-Tax | 2016-03-03
3 | IT | 2016-03-03
6 | Service-Water | 2016-03-03
25 | Service-Water | 2016-03-08
2 | Parks | 2016-04-01
2 | Building | 2016-04-02
3 | Building | 2016-04-15
2 | Development | 2016-04-27
3 | Mayor's Office | 2016-04-28
12 | Court | 2016-05-01
10 | Council | 2016-05-01
35 | Service-Fleet | 2016-05-04
34 | Service | 2016-05-04
37 | Service | 2016-05-13
2 | Council | 2016-05-27
1 | Mayor's Office | 2016-05-27
1 | HR | 2016-06-01
13 | Service-Building | 2016-05-11
5 | Service-Building | 2016-06-28
33 | Parks | 2016-06-28
350 | TOTAL NUMBER OF BOXES DISPOSED OF
*Note: Police typically dispose of their own records
TO BE DISPOSED OF:
BOX COUNT (estimate) | DEPARTMENT | DATE
1 | Council | RC-1 approval
1 | Emergency Management | RC-1 approval
7 | Building | NOT SET YET
35 | Finance | NOT SET YET
35 | HR/CSC | NOT SET YET
20 | Parks | NOT SET YET
99 | TOTAL NUMBER OF BOXES TO BE DISPOSED OF

## FP cost savings
FIREPROOF BOX COST SAVINGS - WORKING DOCUMENT
| FP COST | REMOVED | SAVINGS PER MONTH | Months wasted in FP | Money wasted
.5 cu ft. box | 0.26
1.0 cu ft. box | 0.3
1.5 cu ft. box | 0.46 | 4 | 1.84 | 18 | 33.12
2.0 cu ft. box | 0.6
2.0+ cu ft. box | 0.81